Appendix 4.5	TYPICAL FORMAT OF THE BRIEF FOR AN INVESTIGATION ASSIGNMENT

Agreement No.

BRIEF

1.	Introduction

This Brief is to be read in conjunction with the Memorandum of Agreement, the General Conditions of Employment for an Investigation Assignment, Special Conditions of Employment and Schedule of Fees. For the avoidance of doubt but without prejudice to Clause 7 of the General Conditions of Employment, the performance of the Services specified herein shall be subject to Clause 22 of the General Conditions of Employment.

2.	Description of the Project

Describe the Project of which this Assignment forms a part.  Include relevant historical and general background and any significant events, milestones, policy decisions and other background that may have a bearing on the Assignment.

3.	Objectives of the Assignment

This should follow logically on from section 2 and shall list what is to be achieved upon satisfactory completion of the Assignment.

4.	Description of the Assignment

Describe the Assignment in complete detail.  Make reference not only to what is included but also what is not included.  This is particularly relevant where the scope of the Assignment is different from the scope of the Project described in section 2.	Describe any interfaces between the Assignment and any other parts of the Project or other projects.  Be as specific as possible.

5.	Deliverables

Specify everything that is to be produced by the Consultants as part of the Assignment.  For example, draft reports, final reports, working papers, programmes, estimates, progress and financial reports, design and other calculations, design certificates, minutes of meetings, drawings, plans, maps and models.  Also specify the need to produce documents for the purposes of compliance with statutory procedures, government procedures and consultative procedures.

Specify the numbers of each item to be delivered, the scales for drawings, timing and frequency of delivery and any special requirements for production and method and form of presentation and storage.

Specify the need for the Consultants to draw to the Employer's attention any Deliverables that are under licence and any pre-existing copyright or patent on any Deliverables and any other restriction whatsoever affecting the Employer's use of the same and, if required by the Director's Representative, to establish the existence of any licence, copyright, patent or restriction.

6.	Services to be provided by the Consultants

6.1	Describe all the activities and procedures the Consultants are required to carry out in producing the Deliverables described in section 5.  The following sample clauses provide an indication of the sort of activities and procedures that may be required for an Investigation Assignment.   However, for each particular assignment the wording of the clauses shall be expanded and, where necessary, further clauses shall be added, to describe exactly and in as

much detail as possible what is required.   If the Consultants are to carry out any detailed design work or to 	prepare or manage any substantial investigation, works or supply contracts as part of the Assignment, then 	appropriate clauses relating to such services must be included in the Brief.   Guidance on appropriate clauses can 	be found in the typical format of Brief for a Design and Construction Assignment.

(a)	Carry out or have carried out all necessary surveys, levels and soundings and make such investigations and inquiries as are necessary for  the satisfactory completion of the Assignment.  These shall include but shall not necessarily be limited to (insert specific details of known requirements, if any).

(b)	Prepare and submit a report to the Director's Representative on the results, findings and conclusions of the surveys, levels, soundings, investigations and inquiries carried out under clause (a).

(c)	Direct and control the making or carrying out of boring tests, trial pits, test piles, models, soil investigations and other special investigations, prepare drawings specifications and documents and call for or assist the Employer in calling for tenders or otherwise placing orders for carrying out these works.   These works shall include but shall not necessarily be limited to (insert specific details of known requirements, if any)   (Note, the Schedule of Fees provides for reimbursement of the Consultants in respect of these works).

(d)	Prepare and submit a report to the Director's Representative on the results, findings and conclusions of the tests, trials and investigations carried out under clause (c).

(e)	Identify the need for any resumption, clearance and reprovisioning and liaise with relevant bodies and assist with negotiations for any resumption, clearance and reprovisioning that may be required.

(f)	Identify all facilities, installations and existing rights that may be affected by the Assignment.

(g)	Prepare necessary land requirement plans showing the extent of land requirements for the Assignment.

(h)	Determine the extent of further ground investigations and surveys and further studies required for detailed design purposes.

(i)	Prepare preliminary designs, plans, drawings, profiles, sections, specifications and calculations.

(j)	Prepare a preliminary design for environmental mitigation measures.

(k)	Prepare a sketch landscape design.

(l)	Prepare all necessary documents for the Advisory Committee on the Appearance of Bridges and Associated Structures (ACABAS) submissions.

(m)	Advise the Director's Representative on the types and forms of contract, including Design & Build, most suitable for the implementation of the works.

(n)	Advise the Director's Representative on the number and scope of contracts for implementation of the works.

(o)	Prepare estimates of the cost of works for the Assignment and the contracts including the cost of compensation and reprovisioning.

(p)	Carry out Road Safety Audit for the Project in accordance with the requirements stipulated in the Transport Planning and Design Manual unless otherwise agreed by the Director's Representative. [insert if the Project is new public road project or project with road construction carried out by government departments, where appropriate.]

6.2	Specify the method of reporting and the day-to-day administration of the Assignment. Highlight the timing of meetings and the need for progress reporting.

6.3 	Identify the documents the Consultants must take cognizance of during the Assignment and highlight very important documents.

6.4 	Identify other studies, projects or interface issues which the Consultants must take cognizance of during the Assignment.

6.5 	Identify the bodies, departments, organisations, public utilities and persons with which the Consultants must consult, liaise and coordinate. Indicate the role or purpose of the consultation, liaison or coordination.  Refer to the requirements of Clause 19 of the General Conditions of Employment.

6.6 	Draw to the Consultants attention any specific regulations or ordinances which the Consultants must take account of in providing the Services.

6.7	Specify any need for the Consultants to advise on the formulation and application of criteria for the identification, assessment, evaluation and adoption of options.

6.8	The Consultants shall take cognizance of and comply with relevant requirements of technical circulars and documents issued by the Government bureaux and departments including but not limited to the following:

(a)	EACSB Handbook and other relevant EACSB circulars and circular memoranda;

(b)	General/Technical circulars and other relevant circular memoranda issued by the Development Bureau;

(c)	…..

6.9	The Consultants agree that the management and reporting of the Consultants’ Performance under this Agreement shall be subject to the reporting and management mechanism set out in Development Bureau Technical Circular (Works) Nos. 3/2016 and 5/2018 or its latest revision or replacement.

6.10	Except to the extent otherwise provided for in this Agreement, the Consultants should be responsible for the cost of all computing facilities required by them for fulfilling the obligations under this Agreement.  These computer facilities shall include but not limited to:

(a)	office automation facilities commonly used by secretarial, clerical, administrative, technical or professional staff for the office functions;

(b)	technical computing facilities used by professional and technical staff for computer-aided drafting, computer-aided design and geographical information systems, or other professional systems (such as, but not limited to, Electronic Document Management System, Building Information Modelling, Project Management System) as the case may be; and

(c)	IT training for staff employed by the Consultants.

7.	Response to Queries

The Consultants shall respond to queries under Clause 20 of the General Conditions of Employment raised prior to a date3 months after the final submission of the Deliverables required under the Agreement.   Such date shall be confirmed in writing to the Consultants by the Director's Representative.

8.	Programme of Implementation

8.1	Specify the due date for commencement of the Agreement referred to in Clause 2 of the Schedule of Fees.   The following clause is mandatory.

The due date for commencement of the Agreement is [must be filled in to facilitate pricing by the tenderers pursuant to SoF Clause 2].

8.2	In order to enable consultants to properly estimate a Lump Sum for inclusion in their fee proposal, and to make the submissions comparable, it is necessary that key dates are identified in the Brief to the consultants.  The key dates should be those dates the alteration of which will cause large changes in the consultants' resources input. Although precise information of the key dates may not be available to the writer of the Brief, he shall nevertheless insert the key dates based on his best estimation of events.  After award of the Assignment, the key dates may be changed, upon proposal from the Consultants and agreement by the Director's Representative pursuant to Clause 26(A) of the  General Conditions of Employment.  It is also possible that these key dates may have to be altered during the course of the Assignment as things develop which may, or may not, depending on the circumstances, result in the need to negotiate with the Consultants for additional fees.

Specify the required time table for the various phases of the Assignment, giving key dates and targets.  Describe what is required in the Programme under Clause 26 of the General Conditions of Employment.  The period specified for the submission of and response to the draft programme should be kept as short as practicable.  The following sample Clause, amended to suit the Assignment, shall be included:

Pursuant to Clause 26(B) of the general Conditions of Employment, the Consultants shall submit the draft programme and revised draft programmes and the Directors Representative shall agree, or instruct, within the following periods:

Submission of the draft programme	  :	Within 4 weeks of the date for commencement of the Agreement

Agreement of the draft programme	  :	Within 4 weeks from receipt of the draft programme or instruction for submission of the revised draft programme

Submission of revised draft programme :	Within 2 weeks from the instruction of the Director's Representative

The draft programme and revised draft programmes shall detail the activities to be carried out, target dates for particular tasks and any decision dates that may be required for the uninterrupted progress of the Assignment.  The Consultants shall discuss with the Director's representative during the above periods to agree the timing of submission of reports, other documents and plans for each of the main elements of the Assignment, for inclusion in the draft programme and revised draft programme.

8.3	The key dates referred to in clause 8.2 of this Brief shall include but not be limited to:

(i)	The date of submission of the Draft Report.

(ii)	The date of submission of the Draft Final Report.

Where an ambiguity may arise as to the meaning of any key date included in this section, that key date should be clearly defined in the Brief to avoid ambiguity.

9.	Progress Reports

The Consultants shall submit to the Director's Representative progress reports at ________ intervals on all aspects of the Services relating progress to the Programme referred to in clause 8 of this Brief.  The reports shall include a list of those parts of the Services the execution of which is behind the Programme together with proposals to expedite progress, so as to complete the work on time.  The reports shall also include updated expenditure forecasts in accordance with clause 10 of this Brief.

10.	Financial Management

At ______ intervals or at such other intervals as the Director's Representative may require, the Consultants shall submit a report on the current and forecast expenditure on the Assignment and the fees due to the Consultants, in a form to be agreed by the Director's Representative.

11.	Standards and Specifications

The Consultants shall adopt the following (insert details) and such other technical & design standards and specifications as are in current use by the (insert appropriate names) Department(s) or, if non-existent, British Standard Codes of Practice and Specifications.  Should instances arise for which suitable standards or specifications do not exist or for which the current standards or specifications appear to require modification or if by the adoption of current standards the Consultants would incur additional expenses not within reasonable contemplation, the Consultants shall submit recommendations on appropriate alternatives to the Director's Representative for agreement.

12.	Variations and Other Commitments [Mandatory if the Assignment covers works contracts, the supervision of which is part of the Services]

12.1	The value of a variation to the contract works or other expenditure commitment for the purposes of Clause 24 of the General Conditions of Employment is $800,000.

12.2	All variations to the contract works shall be covered by a variation order in a form to be agreed by the Director's Representative, except that no variation order will be required for increase or decrease in quantities arising from remeasurement of the items in the bills of quantities.

12.3	The Director's Representative shall advise the Consultants of his approval or otherwise under Clause 24 of the General Conditions of Employment within          days of submission.  The reasons for non-approval, which may include insufficiency of supporting information provided with the submission, will be provided to the Consultants at the same time.  If, because of the need for consultation or referral elsewhere, the Director's Representative is unable to give his decision within the period stated then he shall inform the Consultants immediately and advise them of when he will give his decision.  Provided that, in any case, a different period can be applied by mutual agreement.

12.4	Under sub-clause (iii) of Clause 25 of the General Conditions of Employment, the Consultants shall report all claims to the Director's Representative within         days of their receipt.  The Director's Representative shall provide the Employer's views to the Consultants within         days of receipt of the Consultants' principles of assessment of a claim.

12.5	Under sub-clause (iv) of Clause 25 of the General Conditions of Employment, the Consultants shall report all delays to the Director's Representative within         days of the delay being identified.  The Director's Representative shall provide the Employer's views to the Consultants within         days of receipt of the Consultants' assessment of extension of time.

13.	Director's Representative

The Director's Representative as defined in the General Conditions of Employment shall be the ______ (usually specify the post of a D2 officer or above but not lower than D1) or such other person as may be authorised by the Director in writing and notified to the Consultants.  The Director's Representative may delegate any of the powers and functions vested in him to other officers.  If the Consultants are dissatisfied with a decision or instruction of any such officer the matter shall be referred to the Director's Representative for a ruling.

During the course of the Agreement the Consultants shall report direct to the Director's Representative.

14.	Control of the Project and Assignment

List the committees, conferences, boards, and other meetings which the Consultants shall attend, serve or report to, as required by the Director's Representative.   The documents the Consultants shall produce in serving or reporting to these bodies eg. meeting minutes and progress reports shall be stated in section 5 - Deliverables.

15.	Information and Facilities Provided by the Employer

All available information relevant to the Assignment will be provided to the Consultants.  Relevant documents including reports, drawings and other background materials are listed in Appendix ______ to this Brief.  The Consultants shall indicate for guidance those documents which they currently hold and those of which a copy may be needed, should the Assignment be awarded to them.  A copy of each of the documents indicated as needed will be supplied free of charge by the Director's Representative on request from the Consultants, except those currently available from the Sales section of the Information Services Department.   In the case of plans and drawings, one transparency and two prints of each plan or drawing shall be provided free of charge if requested by the Consultants.

16.	Consultants' Office and Staffing

16.1	The Consultants shall maintain for the duration of this Agreement an office in Hong Kong under the control of the Project Director of the Consultants who shall be responsible for the Project.  He shall have adequate authority and sufficient professional, technical and administrative support staff in all relevant disciplines to ensure progress to the satisfaction of the Director's Representative.

16.2	The Consultants shall provide the staff and manpower input in accordance with the Technical Proposal which was submitted with the Consultants’ tender for this Assignment, or the quarterly manpower input updates as stated in sub-clause 6 below if available.  The Director’s Representative shall have the right to check the time-log record of the Consultants’ staff deployed for the Assignment.

16.3	If the Director’s Representative considers that the performance of the Consultants is not satisfactory due to inadequate staffing and manpower input allocated to the Assignment, the Consultants shall, upon the request of the Director’s Representative, forthwith submit to the Director’s Representative the time-log record of the staff deployed for the Assignment for the Director’s Representative to check against the Technical Proposal, or the quarterly manpower input updates as stated in sub-clause 6 below if available.

16.4	The Consultants’ failure to adhere to their staffing proposal, in particular the employment of core personnel of the Consultants and their sub-consultants, thus causing an adverse impact on the performance of the Services, shall be duly reflected in the Employer’s performance report on the Consultants.

16.5	If the Consultants are unable to maintain any of the core personnel specified in the Technical Proposal, the Consultants shall as soon as possible report this to the Director’s Representative and propose, for the Director’s Representative’s approval, a revised personnel arrangement which is equivalent to or better than the existing personnel arrangement, in terms of qualifications, experience and competence.

16.6	The Consultants shall follow the relevant requirements stipulated in Development Bureau Technical Circular (Works) No. 5/2018 or its latest revision or replacement and submit to the Director’s Representative quarterly updates on the manpower input deployed and/or to be deployed by the Consultants under the Assignment for checking and monitoring with the use of Public Works Consultants Resources Allocation Register (PWCRAR) in accordance with the relevant mechanism mentioned in the same technical circular.  The Consultants shall provide clarifications on the manpower input to the Director’s Representative upon request.

16.7	The Consultants agree that the quarterly updates as mentioned in sub-clause 6 above would be inputted into the PWCRAR for purposes as mentioned in the personal information collection statement to be sent to the Consultants with the templates for the quarterly updates, which shall include but not limited to the following:

- activities relating to the management of the status of the Consultant under the List of Consultants (the List) under the purview of the Engineering and Associated Consultants Selection Board (EACSB) of the Government, including any regulating actions against the Consultant such as downgrading, suspension or removal from the List;

- activities relating to the award of consultancies including but not limited to the assessment of the Consultant’s tenders for consultancies;

- activities relating to management of consultancies including but not limited to the monitoring of manpower resources provided and the assessment of Consultant’s performance; and

- compilation of statistical report and diagnosis of problems with or concerning PWCRAR or the management of consultants to help the Government to improve.

17.	Specialist and Sub-consultant Services

17.1	The Consultants shall provide all specialist and sub-consultant services required for the satisfactory completion of the Assignment.  No additional fees or expenses for the provision of such services rendered locally or overseas shall be payable by the Employer except as otherwise provided for in the Schedule of Fees.

17.2	Without derogating from the generality of clause 38(i) of the General Conditions of Employment, the Consultants shall, upon the award of this Agreement and save as otherwise agreed by the Director’s Representative, appoint the sub-consultants as proposed in their Technical Proposal for the Assignment.  The Director’s Representative shall have the right to check the sub-consultancy agreements.  If the Director’s Representative considers that the performance of the Consultants is not satisfactory due to inadequate staffing and manpower input allocated to the Assignment, the Consultants shall, upon the request of the Director’s Representative, forthwith submit to the Director’s Representative a certified copy of any or all of the sub-consultancy agreements.

18.	Surveys

18.1	Two prints of topographical mapping at 1:1000, 1:5000 and 1:20000 scales prepared by the Survey and Mapping Office of the Lands Department, where available for the area covered by the Project for which the Assignment forms a part, can be obtained free of charge on application to the Director's Representative.

18.2	The Consultant may apply for the supply of the series of Digital Map products from Lands Department for the exclusive use of this Assignment free of charge.  Applications should be made to the Director’s Representative by completing and submitting the form “Undertakings by Consultant/Contractor on the Use of Digital Map from Land Information Centre” (SMF-0096) together with a list of the Digital Map products required.  The Consultant is required to provide the storage media for the supply of the Digital Map product files unless Lands Department advises the otherwise.

18.3	All the mapping information provided shall be for the exclusive use of this Assignment.  In using the Digital Map products supplied by Lands Department, the Consultant shall abide by the terms and conditions as stipulated in the undertaking form.  Upon completion of the Assignment, the Consultant shall destroy immediately the supplied Digital Map products and confirm the destruction to Lands Department by completing and returning the form “Confirmation by Government’s Consultant/Contractor on the Cessation of the Use of Digital Map from Land Information Centre” (SMF-0097) to the Director’s Representative within two weeks upon completion of the Assignment.

18.4	All the lot boundary information provided is for identification of the approximate location of lot only and is  subject to amendments by the Lands Department without prior notice. The Consultants shall refer to the District Survey Offices of the Lands Department for the most up-to-date lot boundary information.

18.5	The Consultants shall be responsible for verifying the accuracy and, where necessary, updating all survey and mapping information provided. Unless otherwise provided for in the Assignment, all field survey work required for the proper execution of the Assignment shall be the duty of the Consultants in accordance with        (list any special requirements).  A copy of field notes, field data and resultant plans arising from these surveys shall be handed over to the Director's Representative in hardcopy (paper, transparency and/ or microfilms) and MicroStation (DGN) file format upon completion of the Assignment.  The accuracy as well as presentation of these surveys shall be of a standard agreed by the Director's Representative.  After the Director’s Representative has accepted the survey results, the Consultants shall forward a set of the as-built survey plans in hardcopy and softcopy to the Land Information Centre of the Survey and Mapping Office of the Lands Department.

18.6	The Consultant shall be responsible for submitting drawing computer files which shall be delivered on compact disc in MicroStation (DGN) file format unless otherwise specified by the Director’s Representative. The survey drawings shall be in compliance with the CAD Standard for Works Project (CSWP) version 1.03.00 (or later versions as agreed by the Director’s Representative) as posted on the Development Bureau’s web-site and the Drafting Specification for Engineering Survey Rev 2.0 (or later versions as agreed by the Director’s Representative) as posted on Civil Engineering and Development Department’s web-site.

18.7	Appendix ____ specifies the division of responsibility for other surveying between the Consultants, the Lands Administration Office and Survey and Mapping Office as well as the relevant sub-offices at district level of the  Lands Department. (See Appendix A)

19.	Insurance

The amount of insurance cover to be maintained in accordance with Clause SCExx (the one set out in Appendix 4.17) of the Special Conditions of Employment shall be HONG KONG Dollars _______. (Please follow the procedures for the procurement of Professional Indemnity Insurance and the methodology for determining the amount of insurance cover given in DEVB TCW No. 9/2007and state the assessed amount of the insurance cover in terms of the lump sum fee, subject to minimum and maximum values, as appropriate.)

Appendix A

AGREEMENT NO.

Responsibility for Survey Work

The division of responsibility among the Consultants, the Lands Administration Office, and the Survey and Mapping Office of the Lands Department for surveying required in connection with the Assignment shall be as follows :-

| Task | Responsibility of |
| --- | --- |
| (1) (a) Provision of basic horizontal and vertical survey control | Survey and Mapping Office (Consultants to download from www.geodetic.gov.hk) |
| (b) Checking of given control point values and establishment of survey control net-work(s) based on survey control given vide (a) | Consultants |
| (2) (a) Provision of topographic maps (at 1:1000 or other standard scales relevant to the Assignment) | Survey and Mapping Office (excluding those specified as to be provided by the Consultants in the Assignment) |
| (b) Provision of available Digital Map products relevant to the Assignment | Land Information Centre, Survey and Mapping Office |
| (c) Updating and verification of accuracy of information supplied vide (a) and (b) as necessary in relation to the Assignment | Consultants |
| (d) Carrying out detailed surveys for site investigation and for preparation of design and contract documents as necessary in relation to the Assignment | Consultants |
| (3) Supply of existing cadastral plans and records and co-ordinate data | District Survey Office |
| (4) Computation of detailed dimensioned layouts of roads, drainage and waterworks reserves, platforms, etc. | Consultants (checked and accepted by District Survey Office) |
| (5) Determination of site/lot boundaries, calculation of areas, etc. in connection with the agreed dimensioned layouts | District Survey Office (in liaison with District Lands Office) |
| (6) (a) Processing of resumption and surrender for privately owned land in Development Area | District Lands Office (in liaison with District Survey Office and Consultants) |
| (b) Resumption and surrender plans and demarcation of lands to be resumed | District Survey Office (in liaison with District Lands Office and Consultants) |
| Task | Responsibility of |
| (7) (a) Setting-out of roads, drainage works, formation areas, etc. | Contractors (checked and accepted by Consultants, usually by resident site staff under their supervision.) |
| (b) Initial site survey, and interim and final payment surveys | Consultants, usually by resident site staff under their supervision (joint survey with contractors or agreed survey with contractors) |
| (8) Preparation of proposal plans for Government land allocations and other land grants relevant to the Assignment | District Survey Office (in liaison with District Lands Office) |
| (9) Preparation of dimensioned plans and setting out of boundaries of sites and lots for Government land allocation and for other land grants relevant to the Assignment | District Survey Office |
| (10) As-built surveys (including records of positions and levels on all underground pipelines, etc.) | Consultants, usually by resident site staff under their supervision. |
| (11) Supply a set of as-built survey plans in both hardcopy and softcopy to the Land Information Centre of the Survey and Mapping Office of the Lands Department | Consultants, usually by resident site staff under their supervision. |